## Clean_data_FIXED
sl_no | request_date | request_number | part | part_number | equipment_or_vehicle | brand | model | rg_number | reqd_count | qty | received_part_no | recd_count | left_count | status | receive_number | recived_date | return_mir | return_date
1 |  | 750 |  |  | Roller compactor | Ammann |  | 292.077 | 1 | Nos |  | 1 | 0 | Arrivel Date | 108 | 2025-08-09
2 |  | 750 |  |  | Roller compactor | Ammann |  | 292.078 | 1 | Nos |  | 1 | 0 | Arrivel Date | 108 | 2025-08-09
3 |  | 312 | Empty Steel Drum | [5 empty] | 1 | Nos |  | 1 | 0 | Not Requested | 5 | 2025-08-13
4 |  | 799 |  |  | 4.2 ton pick up | Izuzu | Canter | 31545 | 1 | Nos |  | 1 | 0 | Arrivel Date | 112 | 2025-08-30
5 |  | 310 |  |  | Bar cutting mechine |  |  | 487.108 | 1 | Nos |  | 1 | 0 | Arrivel Date | 114 | 2025-08-30
6 |  | 310 |  |  | Bar bending mechine |  |  | 488.1 | 1 | Nos |  | 1 | 0 | Arrivel Date | 114 | 2025-08-30
7 |  | 312 | Empty Steel Drum | [5 empty] | 2 | Nos |  | 2 | 0 | Not Requested | 24 | 2025-09-01
8 |  | 328 | Generator and Dip Tray |  | Genarator | Perkins |  | 191.315 | 1 | Nos |  | 1 | 0 | Arrivel Date | 118 | 2025-09-01
9 |  | 95100 50424 | Cargo belt | [5 empty] | 4 | Nos |  | 4 | 0 | Not Requested | 10 | 2025-09-04
10 |  | 803 |  |  | Back hoe Loader | JCB | 3 DX | 289.018 | 1 | Nos |  | 1 | 0 | Arrivel Date | 122 | 2025-09-11
11 |  | 803 |  |  | Skid Steer Loader | Case | SR130B | 292.089 | 1 | Nos |  | 1 | 0 | Arrivel Date | 122 | 2025-09-11
12 |  | 296 |  |  | Air compressor | ATLAS COPCO | T250-7 | 190.104 | 1 | Nos |  | 1 | 0 | Arrivel Date | 124 | 2025-09-09
13 |  | 296 | Air hose 3/11 X 50 METER | [5 empty] | 2 | Nos |  | 2 | 0 | Not Requested | 12 | 2025-09-09
14 |  | 296 | Hose front 3/11 | [5 empty] | 10 | Nos |  | 10 | 0 | Not Requested | 12 | 2025-09-09
15 |  | 296 | Double bIlt clamp 3/11 | [5 empty] | 10 | Nos |  | 10 | 0 | Not Requested | 12 | 2025-09-09
16 |  | 296 | Whip Click | [5 empty] | 10 | Nos |  | 10 | 0 | Not Requested | 12 | 2025-09-09
17 |  | 296 | Rubber WASHER | [5 empty] | 10 | Nos |  | 10 | 0 | Not Requested | 12 | 2025-09-09
18 |  | 296 | THREAD COMPILER | [5 empty] | 10 | Nos |  | 10 | 0 | Not Requested | 12 | 2025-09-09
19 |  | 522 | Accelerator cable | [5 empty] | 2 | Nos |  | 2 | 0 | Not Requested | 32 | 2025-11-20
20 |  | 522 | Power Float Blade | [5 empty] | 5 | Set |  | 5 | 0 | Not Requested | 32 | 2025-11-20
21 |  | 398 | Armored Cable 41 x 150mm2 | [5 empty] | 20 | M |  | 20 | 0 | Not Requested | 13 | 2015-09-21
22 |  | 398 | Armored Cable 41 x 130mm2 | [5 empty] | 40 | M |  | 40 | 0 | Not Requested | 13 | 2015-09-21
23 |  | 398 | Earth cable 150 mm2 | [5 empty] | 35 | M |  | 35 | 0 | Not Requested | 13 | 2015-09-21
24 | 2025-10-15 | 234 | Flat trailer | 30024 |  |  |  |  | 1 | Nos |  | 1 | 0 | Not Requested | 28 | 2025-11-12
25 | 2025-10-15 | 234 | Heavy load Unit |  | unit | Benz | Actros | 76953 | 1 | Nos |  | 1 | 0 | Arrivel Date | 156 | 2025-11-12
26 | 2025-11-03 | 380 | DIESEL Engine Tower Light |  | Diesel Tower Light | Trex | RL 4000 | 191.124 | 1 | Nos |  | 1 | 0 | Arrivel Date | 158 | 2025-11-13
27 | 2025-11-03 | 380 | DIESEL Engine Tower Light |  | Diesel Tower Light | Trex | RL 4000 | 191.125 | 1 | Nos |  | 1 | 0 | Arrivel Date | 158 | 2025-11-13
28 | 2025-11-07 | 380 | Genarator with third part and dip tray |  | Genarator | Weichai | 20 KWA | 191.417 | 1 | Nos |  | 1 | 0 | Arrivel Date | 158 | 2025-11-13
29 | 2025-11-07 | 380 | Genarator with third part and dip tray |  | Genarator | Weichai | 80 KWA | 191.424 | 1 | Nos |  | 1 | 0 | Arrivel Date | 158 | 2025-11-13
30 | 2025-11-07 | 380 | Genarator with third part and dip tray |  | Genarator | Weichai | 30 KWA | 191.426 | 1 | Nos |  | 1 | 0 | Arrivel Date | 158 | 2025-11-13
31 |  | 802 | Genarator Replacement for hired with drip tray |  | Genarator | Perkins | JP 12.5 | 191.227 | 1 | Nos |  | 1 | 0 | Arrivel Date | 134 | 2025-10-07
32 |  | 802 | Genarator Replacement for hired with drip tray |  | Genarator | Perkins | JP 20 | 191.264 | 1 | Nos |  | 1 | 0 | Arrivel Date | 134 | 2025-10-07
33 |  | 278 | Diesel tank with all accessories and flow meter |  | Diesel Tank |  | 10000 gallon | 389.003 | 1 | Nos |  | 1 | 0 | Arrivel Date | 136 | 2025-10-17
34 |  | 278 | Empty Steel Drum | [5 empty] | 2 | Nos |  | 2 | 0 | Not Requested | 18 | 2025-10-17
35 |  | 234 | Tele Handler model 540-170 with bucket and fork,complaint,Third party |  | BoomLoader | Merlo | P27 | 290.029 | 1 | Nos |  | 1 | 0 | Arrivel Date | 140 | 2025-10-27
36 |  | 312 | Empty Steel Drum | [9 empty] | 0 | Not Requested | 24 | 2025-10-31
|  | 398 | Empty Steel Drum | [5 empty] | 2 | Nos |  | 2 | 0 | Not Requested | 13 | 2015-09-21
37 | 2025-09-15 | 173724 | Eletrical Air Compressor | [5 empty] | 1 | Nos |  | 1 | 0 | complete | 128 | 2025-10-04
38 | 2025-09-15 | 173724 | Air Hose 3/8 | [5 empty] | 1 | Nos | 25 M | 1 | 0 | complete | 128 | 2025-10-04
39 | 2025-09-15 | 173724 | Screw Driver set | [5 empty] | 1 | Nos |  | 1 | 0 | complete | 144 | 2025-10-28
40 | 2025-09-15 | 173724 | Allen Key set .7mm to 17mm | [5 empty] | 1 | Nos |  | 1 | 0 | complete | 144 | 2025-10-28
43 | 2025-09-15 | 173724 | Air Checking Gauge | [5 empty] | 1 | Nos |  | 1 | 0 | complete | 144 | 2025-10-28
44 | 2025-09-15 | 173724 | Tyre Repair Kit | [5 empty] | 1 | Nos |  | 1 | 0 | complete | 146 | 2025-10-28
45 | 2025-09-15 | 173724 | Puncher seal Kit Big | Puncher kit Arived was tube less |  |  |  |  | 2 | Packs |  | 2 | 0 | complete | 146 | 2025-10-28
46 | 2025-09-15 | 173724 | Puncher seal Kit Small | [5 empty] | 2 | Packs |  | 2 | 0 | complete | 146 | 2025-10-28
47 | 2025-09-15 | 173724 | Filter Wrench Belt | [5 empty] | 1 | Nos |  | 1 | 0 | complete | 146 | 2025-10-28
48 | 2025-09-15 | 173726 | Hand Roatary Pump | [5 empty] | 2 | Nos |  | 2 | 0 | complete | 146 | 2025-10-28
49 | 2025-09-15 | 173726 | Oil Measuring can | [5 empty] | 2 | Nos |  |  | 2 | left
50 | 2025-09-15 | 173726 | Grip Piler | [5 empty] | 1 | Nos |  | 1 | 0 | complete | 144 | 2025-10-28
51 | 2025-09-15 | 173726 | Comp Piler | [5 empty] | 1 | Nos |  | 1 | 0 | complete | 144 | 2025-10-28
52 | 2025-09-15 | 173726 | Hand grease pump | [5 empty] | 1 | Nos |  | 1 | 0 | complete | 146 | 2025-10-28
53 | 2025-09-15 | 173726 | High Pressure Water Pump | [5 empty] | 1 | Nos |  |  | 1 | left
54 | 2025-09-15 | 173726 | Rubber Hammer | [5 empty] | 1 | Nos |  | 1 | 0 | complete | 146 | 2025-10-28
55 | 2025-09-15 | 173726 | Bearing Puller | [5 empty] | 1 | Nos |  | 1 | 0 | complete | 146 | 2025-10-28
56 | 2025-09-15 | 173726 | Grese Nipple Box | [5 empty] | 1 | Nos |  |  | 1 | left
57 | 2025-09-15 | 173726 | O Ring Kit | [5 empty] | 1 | Nos |  | 1 | 0 | complete | 162 | 2025-11-17
58 | 2025-09-15 | 173726 | Stainless Steel Circlip set /Snap ring Set | [5 empty] | 1 | Nos |  |  | 1 | complete
59 | 2025-09-15 | 173726 | Snap Ring Piler | [5 empty] | 2 | Nos | Lock piler set | 1 | 1 | left | 31 | 2025-11-17
60 | 2025-09-15 | 173726 | Crocdile Jack 5 Ton | [5 empty] | 1 | Nos |  | 1 | 0 | complete | 144 | 2025-10-28
61 | 2025-09-16 | 173718 | Container with A/c | [5 empty] | 1 | Nos |  | 1 | 0 | complete | 600 | 2026-01-23
62 | 2025-10-08 | 177702 | Starter coil |  | Diesel Vibrator |  | 173 f /00120 |  | 2 | Nos |  | 2 | 0 | complete | 144 | 2025-10-28
63 | 2025-10-08 | 177702 | Starter rope |  | Diesel Vibrator |  | 173 f /00120 |  | 1 | Nos |  | 1 | 0 | complete | 144 | 2025-10-28
64 | 2025-10-08 | 177702 | Accelerator |  | Plate Compactors |  | D 230F |  | 1 | Nos |  | 1 | 0 | complete | 144 | 2025-10-28
65 | 2025-10-08 | 177708 | IVMS installation |  | Car |  | Pajero | 72974 | 1 | Nos |  |  | 1 | Services
66 | 2025-10-11 | 177720 | Third Party |  | Solar Tower Light |  |  | 191.353 | 1 | Nos |  |  | 1 | Services
67 | 2025-10-11 | 177720 | Third Party |  | Solar Tower Light |  |  | 191.407 | 1 | Nos |  |  | 1 | Services
68 | 2025-10-11 | 177720 | Third Party |  | Solar Tower Light |  |  | 191.408 | 1 | Nos |  |  | 1 | Services
69 | 2025-10-11 | 177720 | Third Party |  | Solar Tower Light |  |  | 191.409 | 1 | Nos |  |  | 1 | Services
70 | 2025-10-11 | 177720 | Third Party |  | Solar Tower Light |  |  | 191.345 | 1 | Nos |  |  | 1 | Services
71 | 2025-10-11 | 177720 | Third Party |  | Solar Tower Light |  |  | 191.349 | 1 | Nos |  |  | 1 | Services
72 | 2025-10-11 | 177720 | Third Party |  | Solar Tower Light |  |  | 191.371 | 1 | Nos |  |  | 1 | Services
73 | 2025-10-11 | 177720 | Third Party |  | Solar Tower Light |  |  | 191.372 | 1 | Nos |  |  | 1 | Services
74 | 2025-10-11 | 177720 | Third Party |  | Solar Tower Light |  |  |  | 1 | Nos |  |  | 1 | Services
75 | 2025-09-15 | 173728 | Magnetic stick | [5 empty] | 1 | Nos |  | 1 | 0 | complete | 152 | 2025-11-10
76 | 2025-09-15 | 173728 | Hammer Set | One PCS from each type |  |  |  |  | 1 | Nos |  | 4 | -3 | complete | 172 | 2025-12-09
77 | 2025-09-15 | 173728 | Air pressure gun small | [5 empty] | 1 | Nos |  | 1 | 0 | complete | 152 | 2025-11-10
78 | 2025-09-15 | 173728 | Air pressure gun Big | [5 empty] | 1 | Nos |  |  | 1 | left
79 | 2025-09-16 | 173732 | Dip tray 2M X 2M | [5 empty] | 1 | Nos |  |  | 1 | left
80 | 2025-09-16 | 173732 | Dip tray 1M X50 cm | [5 empty] | 1 | Nos |  |  | 1 | left
81 | 2025-09-16 | 173734 | Engine Oil |  |  |  | 15W/40 |  | 1 | Nos |  | 1 | 0 | complete | 152 | 2025-11-10
82 | 2025-09-16 | 173734 | Hydrolic oil | [5 empty] | 1 | Nos |  | 1 | 0 | complete | 152 | 2025-11-10
83 | 2025-09-16 | 173734 | Grease EP2 | [5 empty] | 15 | KG |  | 15 | 0 | complete | 152 | 2025-11-10
84 | 2025-09-16 | 173734 | Coolent | [5 empty] | 1 | Nos |  | 1 | 0 | complete | 168 | 2025-11-22
85 | 2025-09-16 | 173734 | Break oil | [5 empty] | 2 | L |  | 2 | 0 | Complete | 26 | 2025-11-10
86 | 2025-10-02 | 173784 | IVMS installation |  | unit | Benz | Actros | 76953 | 1 | Nos |  |  | 1 | Services
87 | 2025-10-20 | 177740 | Battery 80D26L | [5 empty] | 1 | Nos |  | 1 | 0 | Complete | 26 | 2025-11-10
88 | 2025-10-20 | 177740 | Bulb |  |  |  | H7 |  | 10 | Nos |  |  | 10 | left
89 | 2025-10-20 | 177740 | D.Rust Spray | [5 empty] | 10 | Nos |  | 10 | 0 | Complete | 26 | 2025-11-10
90 | 2025-10-20 | 177740 | Grease EP2 | 15 Kg |  |  |  |  | 1 | Nos |  | 1 | 0 | complete | 174 | 2025-12-16
91 | 2025-10-20 | 177740 | Grease gun | [5 empty] | 1 | Nos |  |  | 1 | left
92 | 2025-10-20 | 177740 | Oil filter | 2654403 | Genarator | Perkins | JP 60 | 191.315 | 4 | Nos |  | 4 | 0 | complete | 152 | 2025-11-10
93 | 2025-10-20 | 177740 | Fuel filter | 4461492 | Genarator | Perkins | JP 60 | 191.315 | 2 | Nos | 1000 70419 | 2 | 0 | complete | 150 | 2025-11-10
94 | 2025-10-20 | 177740 | Air Filter | 26510337 | Genarator | Perkins | JP 60 | 191.315 | 2 | Nos | C14210 | 1 | 1 | left | 26 | 2026-11-10
95 | 2025-10-20 | 177740 | Oil filter | 140517050 | Genarator | Perkins | JP 20 | 191.227 | 8 | Nos | W712/98 | 8 | 0 | complete | 152 | 2025-11-10
96 | 2025-10-20 | 177740 | Fuel filter | 4415122 | Genarator | Perkins | JP 20 | 191.227 | 4 | Nos |  |  | 4 | left
97 | 2025-10-20 | 177740 | Air Filter | 5543095 | Genarator | Perkins | JP 20 | 191.227 | 1 | Nos | 26510343 |  |  | complete | 150 | 2025-11-10
98 | 2025-10-20 | 177740 | Oil filter | 140517050 | Genarator | Perkins | JP 12.5 | 191.264 | 8 | Nos |  |  | 8 | left
99 | 2025-10-20 | 177740 | Fuel filter | 4415122 | Genarator | Perkins | JP 12.5 | 191.264 | 4 | Nos |  |  | 4 | left
100 | 2025-10-20 | 177740 | Air Filter | 5543091 | Genarator | Perkins | JP 12.5 | 191.264 | 1 | Nos |  | 1 | 0 | complete | 150 | 2025-11-10
101 | 2025-10-30 | 177756 | IVMS installation |  | 1.5 Ton Pickup | Toyto | Hilux | 27671 | 1 | Nos |  |  | 1 | Services
102 | 2025-10-30 | 177756 | IVMS installation |  | 1.5 Ton Pickup | Toyto | Hilux | 27672 | 1 | Nos |  |  | 1 | Services
103 | 2025-10-30 | 177756 | IVMS installation |  | 1.5 Ton Pickup | Toyto | Hilux | 27673 | 1 | Nos |  |  | 1 | Services
104 | 2025-10-30 | 177756 | IVMS installation |  | 1.5 Ton Pickup | Toyto | Hilux | 27674 | 1 | Nos |  |  | 1 | Services
105 | 2025-10-30 | 177756 | IVMS installation |  | 1.5 Ton Pickup | Toyto | Hilux | 27675 | 1 | Nos |  |  | 1 | Services
106 | 2025-10-30 | 177756 | IVMS installation |  | 1.5 Ton Pickup | Toyto | Hilux | 27676 | 1 | Nos |  |  | 1 | Services
107 | 2025-10-30 | 177756 | IVMS installation |  | 1.5 Ton Pickup | Toyto | Hilux | 27677 | 1 | Nos |  |  | 1 | Services
108 | 2025-10-30 | 177756 | IVMS installation |  | 1.5 Ton Pickup | Toyto | Hilux | 27678 | 1 | Nos |  |  | 1 | Services
109 | 2025-11-03 | 177760 | Battery | 80D26L | 1.5 Ton Pickup | Toyto | Hilux | 72974 | 2 | Nos | 70A | 2 | 0 | complete | 152 | 2025-11-10
110 | 2025-11-03 | 177760 | Jumping Cable | [5 empty] | 1 | Nos |  |  | 1 | left
111 | 2025-11-03 | 177766 | clutch Assy |  | Plate Compactors |  |  | 120211031484 | 1 | Nos |  |  | 1 | left
112 | 2025-11-03 | 177766 | Belt |  | Plate Compactors |  |  | 120211031484 | 4 | Nos |  |  | 4 | left
113 | 2025-11-03 | 177766 | Bolt For Clutch |  | Plate Compactors |  |  | 120211031484 | 2 | Nos |  |  | 2 | left
114 | 2025-11-03 | 177766 | Thread Lock |  | Plate Compactors |  |  | 120211031484 | 2 | Nos |  |  | 2 | left
115 | 2025-11-03 | 177766 | Gasket Silcon |  | Plate Compactors |  |  | 120211031484 | 4 | Nos |  |  | 4 | left
116 | 2025-11-03 | 177766 | Gasket Sheet |  | Plate Compactors |  |  | 120211031484 | 1 | Nos |  |  | 1 | left
117 | 2025-11-03 | 177766 | Starting coil Assembly |  | Vibrator |  |  |  | 2 | Nos |  |  | 2 | left
118 | 2025-11-03 | 177766 | Oil filter |  | Air compressor | ATLAS COPCO | T250-7 |  | 3 | Nos |  |  | 3 | left
119 | 2025-11-03 | 177766 | Fuel Filter | 1092-1007.00 | Air compressor | ATLAS COPCO | T250-7 |  | 3 | Nos |  |  | 3 | left
120 | 2025-11-03 | 177766 | Fuel Water Separator | 1094-14719.00 | Air compressor | ATLAS COPCO | T250-7 |  | 1 | Nos |  |  | 1 | left
121 | 2025-11-03 | 177766 | Air Filter Compressor | 1092-5280.00 | Air compressor | ATLAS COPCO | T250-7 |  | 1 | Nos |  |  | 1 | left
122 | 2025-11-03 | 177766 | Air filter Engine | 16130118-01 | Air compressor | ATLAS COPCO | T250-7 |  | 1 | Nos |  |  | 1 | left
123 | 2025-11-03 | 177766 | Air Filter Inner | 16363017.95 | Air compressor | ATLAS COPCO | T250-7 |  | 1 | Nos |  |  | 1 | left
124 | 2025-11-03 | 177768 | Air filter |  | Diesel Vibrator |  |  |  | 4 | Nos |  |  | 4 | left
125 | 2025-11-03 | 177768 | Air filter |  | Plate Compactors |  |  |  | 2 | Nos |  |  | 2 | left
126 | 2025-11-03 | 177768 | Air filter |  | Roller Compactor |  |  |  | 2 | Nos |  |  | 2 | left
127 | 2025-11-03 | 177768 | Oil filter | 320/B4420 | BoomLoader | Merlo | P27 |  | 3 | Nos |  | 3 | 0 | complete | 170 | 2025-11-28
128 | 2025-11-03 | 177768 | Fuel filter | 320/A7170 | BoomLoader | Merlo | P27 |  | 1 | Nos | 10K936 | 1 | 0 | complete | 154 | 2025-11-11
129 | 2025-11-03 | 177768 | Fuel Water Separator | 320/a/7124 | BoomLoader | Merlo | P27 |  | 1 | Nos |  | 1 | 0 | left
130 | 2025-11-03 | 177768 | Air filter(Outer) | 32/917804 | BoomLoader | Merlo | P27 |  | 1 | Nos |  | 1 | 0 | left
131 | 2025-11-03 | 177768 | Air filter(Inner) | 32/917805 | BoomLoader | Merlo | P27 |  | 1 | Nos | CF400 | 1 | 0 | complete | 154 | 2025-11-11
132 | 2025-11-03 | 177768 | Hydrolic Filter | 320/A7170 | BoomLoader | Merlo | P27 |  | 1 | Nos |  |  | 1 | left
133 | 2025-11-03 | 177768 | Transmission filter | 581/M8563 | BoomLoader | Merlo | P27 |  | 1 | Nos |  | 1 | 0 | complete | 170 | 2025-11-28
134 |  | 95100 50424 | Strainer Filter | 332/B1918 | BoomLoader | Merlo | P27 |  | 0 |  |  | 1 | -1 | Exceed | 35 | 2025-11-28
| 2025-11-03 | 177768 | A/C Filter | 33/cz305 | BoomLoader | Merlo | P27 |  | 1 | Nos |  | 1 | 0 | complete | 170 | 2025-11-28
135 | 2025-11-03 | 177770 | Oil Filter | 6675517 | Skid Steer Loader | Case | SR130B |  | 3 | Nos |  | 4 | -1 | Exceed | 26 | 2025-11-10
136 | 2025-11-03 | 177770 | Fuel filter | 66675517 | Skid Steer Loader | Case | SR130B |  | 1 | Nos |  | 2 | -1 | Exceed | 26 | 2025-11-10
137 | 2025-11-03 | 177770 | Fuel Water Separator | 6667352 | Skid Steer Loader | Case | SR130B |  | 1 | Nos |  | 4 | -3 | Exceed | 26 | 2025-11-10
138 | 2025-11-03 | 177770 | Air filter(Inner) | 6666376 | Skid Steer Loader | Case | SR130B |  | 1 | Nos |  | 2 | -1 | Exceed | 26 | 2025-11-10
139 | 2025-11-03 | 177770 | Air filter(Outer) | 6666375 | Skid Steer Loader | Case | SR130B |  | 1 | Nos |  | 4 | -3 | Exceed | 26 | 2025-11-10
140 | 2025-11-03 | 177770 | Hydraulic Filter | 7319444 | Skid Steer Loader | Case | SR130B |  | 1 | Nos |  | 2 | -1 | Exceed | 26 | 2025-11-10
141 | 2025-11-03 | 177774 | Third Party | Flat Trailer | Trailer | Hino | 2045 | 76953 | 1 | Nos |  |  | 1 | Services
142 | 2025-11-12 | 178104 | First aid Box Big | [5 empty] | 4 | Nos |  | 4 | 0 | complete | 166 | 2025-11-21
143 | 2025-11-12 | 178104 | First AID Box Small | [5 empty] | 9 | Nos |  | 4 | 5 | left | 34 | 2025-11-22
144 | 2025-11-12 | 178104 | Reflective Safty Triangle |  | unit | Benz | Actros | 76953 | 1 | Nos |  | 1 | 0 | complete | 168 | 2025-11-22
145 | 2025-11-12 | 178104 | Jack | Jack 20 ton | unit | Benz | Actros | 76953 | 1 | Nos |  | 1 | 0 | complete | 172 | 2025-12-09
146 | 2025-11-19 | 178118 | Oil filter | 5850 | Genarator | Weichai | HP 80 | 191.424 | 3 | Nos | GLF 41006 | 3 | 0 | complete | 202 | 2026-01-22
147 | 2025-11-19 | 178118 | Fuel filter | 1000665-142 | Genarator | Weichai | HP 80 | 191.424 | 3 | Nos | GFF821 | 2 | 1 | left | 51 | 2026-01-22
148 | 2025-11-19 | 178118 | Fuel Water Separator | 10008 71108 | Genarator | Weichai | HP 80 | 191.424 | 3 | Nos | F 51095 | 2 | 1 | left | 51 | 2026-01-22
149 | 2025-11-19 | 178118 | Air Filter | 10001069804/1447 | Genarator | Weichai | HP 80 | 191.424 | 3 | Nos | AF 25258 | 2 | 1 | left | 51 | 2026-01-22
150 | 2025-11-19 | 178118 | Oil filter | 1001 740614 | Genarator | Weichai | HP 30 | 191.426 | 3 | Nos | GLF 41363 | 2 | 1 | left | 51 | 2026-01-22
151 | 2025-11-19 | 178118 | Fuel filter | 1000 622860 | Genarator | Weichai | HP 30 | 191.426 | 3 | Nos | GFF821 | 3 | 0 | complete | 202 | 2026-01-22
152 | 2025-11-19 | 178118 | Air Filter | 1000 940409 | Genarator | Weichai | HP 30 | 191.426 | 3 | Nos | GLF 40824 | 3 | 0 | complete | 202 | 2026-01-22
153 | 2025-11-19 | 178118 | Oil filter | 1001 740614 | Genarator | Weichai | HP 20 | 191.417 | 3 | Nos | GLF 41363 | 2 | 1 | left | 51 | 2026-01-22
154 | 2025-11-19 | 178118 | Fuel filter | 1000 622860 | Genarator | Weichai | HP 20 | 191.417 | 3 | Nos | GFF821 | 3 | 0 | complete | 202 | 2026-01-22
155 | 2025-11-19 | 178118 | Air Filter | 1000 940409 | Genarator | Weichai | HP 20 | 191.417 | 3 | Nos | GLF 40824 | 3 | 0 | complete | 202 | 2026-01-22
156 | 2025-11-20 | 178126 | Third Party |  | Crane | Sany | 60 ton | 286.036 | 2 | Nos |  |  | 2 | Services
157 | 2025-11-20 | 178126 | Third Party |  | Crane | Sany | 60 ton | 286.039 | 2 | Nos |  |  | 2 | Services
158 | 2025-11-20 | 178128 | Oil filter | 15163-EV052 | unit | Benz | Actros | 76953 | 1 | Nos |  | 1 | 0 | complete | 170 | 2025-11-28
159 | 2025-11-20 | 178128 | Oil filter | 15613-EV043 | unit | Benz | Actros | 76953 | 1 | Nos | 01560 72281 | 1 | 0 | complete | 172 | 2025-12-09
160 | 2025-11-20 | 178128 | Fuel filter | 23304-EV351 | unit | Benz | Actros | 76953 | 1 | Nos | 02340 11580 | 1 | 0 | complete | 170 | 2025-11-28
161 | 2025-11-20 | 178128 | Fuel Water Separator | 23304-EV140 | unit | Benz | Actros | 76953 | 1 | Nos |  |  | 1 | left
162 | 2025-11-20 | 178128 | Air filter(Inner) | 17801-EW060 | unit | Benz | Actros | 76953 | 1 | Nos |  | 1 | 0 | complete | 170 | 2025-11-28
163 | 2025-11-20 | 178128 | Air filter(Outer) | 17801-EW050 | unit | Benz | Actros | 76953 | 1 | Nos | 017801 3450 | 1 | 0 | complete | 172 | 2025-12-09
164 | 2025-11-20 | 178128 | Air filter(Inner) | 17801-EW060 | unit | Benz | Actros | 76953 | 1 | Nos | 017801 3460 | 1 | 0 | Not Requested | 36 | 2025-12-09
165 | 2025-11-20 | 178128 | Battery cuttoff Switch |  | Skid Steer Loader | Case | SR130B | 292.089 | 1 | Nos |  | 1 | 0 | complete | 170 | 2025-11-28
166 | 2025-11-25 | 178142 | Trailer truck Air hose | Red | unit | Benz | Actros |  | 1 | Nos |  | 1 | 0 | complete | 180 | 2025-12-29
167 | 2025-11-25 | 178142 | Trailer truck Air hose | Yellow | unit | Benz | Actros |  | 1 | Nos |  | 1 | 0 | complete | 180 | 2025-12-29
168 | 2025-11-25 | 178142 | Female Adapter and Coupling |  | unit | Benz | Actros |  | 2 | Nos |  | 2 | 0 | complete | 180 | 2025-12-29
169 | 2025-11-25 | 178142 | Epoxy | [5 empty] | 1 | Nos | Steel Epoxy | 1 | 0 | complete | 172 | 2025-12-09
170 | 2025-11-25 | 178142 | Warnig Light | 12V/24V |  |  |  |  | 4 | Nos |  |  | 4 | left
171 | 2025-12-12 | 178702 | Starting coil |  | Diesel Vibrator |  | 173 F | BCC-001 | 2 | Nos |  |  | 2 | left
172 | 2025-12-12 | 178702 | clutch Assembly and bolt |  | Plate Compactors |  | pp-120 | BCC-001 | 1 | Nos |  |  | 1 | left
173 | 2025-12-12 | 178702 | Thread Lock paste | [5 empty] | 3 | Nos |  |  | 3 | left
174 | 2025-12-12 | 178702 | Starting Coil |  | Plate Compactors |  | pp-120 | BCC-001 | 1 | Nos |  |  | 1 | left
175 | 2025-12-12 | 178702 | Oil filter |  | Back hoe Loader | JCB | 3 DX | 289.108 | 1 | Nos |  |  | 1 | left
176 | 2025-12-12 | 178702 | Fuel filter |  | Back hoe Loader | JCB | 3 DX | 289.108 | 1 | Nos |  |  | 1 | left
177 | 2025-12-12 | 178702 | Air filter(Inner) | 47362227 | Back hoe Loader | JCB | 3 DX | 289.108 | 1 | Nos |  |  | 1 | left
178 | 2025-12-12 | 178702 | Air filter(Outer) | 47362223 | Back hoe Loader | JCB | 3 DX | 289.108 | 1 | Nos |  |  | 1 | left
179 | 2025-12-12 | 178702 | Hydraulic Filter |  | Back hoe Loader | JCB | 3 DX | 289.108 | 1 | Nos |  |  | 1 | left
180 | 2025-12-12 | 178702 | Transmission filter |  | Back hoe Loader | JCB | 3 DX | 289.108 | 1 | Nos |  |  | 1 | left
181 | 2025-12-12 | 178702 | A/C Filter |  | Back hoe Loader | JCB | 3 DX | 289.108 | 1 | Nos |  |  | 1 | left
182 | 2025-12-12 | 178702 | Fuel Water Separator | 47801835 | Back hoe Loader | JCB | 3 DX | 289.108 | 1 | Nos |  |  | 1 | left
183 | 2025-12-13 | 178186 | Starter Coil |  | Diesel Vibrator |  | 173 F |  | 2 | Nos | Recoil Starter | 2 | 0 | complete | 196 | 2026-01-10
184 | 2025-12-13 | 178186 | Clutch Assembly |  | Diesel Vibrator |  | 173 F |  | 1 | Nos |  |  | 1 | left
185 | 2025-12-13 | 178186 | Thread Lock paste |  |  |  | 173 F |  | 3 | Nos |  |  | 3 | left
186 | 2025-12-13 | 178186 | Starter Coil |  | Plate Compactors |  | pp-120 |  | 1 | Nos | Recoil Starter | 1 | 0 | complete | 196 | 2026-01-10
187 | 2025-12-15 | 178192 | Oil filter | 320/B4420 | BoomLoader | Merlo | P27 |  | 4 | Nos |  | 4 | 0 | complete | 182 | 2025-12-29
188 | 2025-12-15 | 178192 | Fuel filter | 320/A7170 | BoomLoader | Merlo | P27 |  | 2 | Nos |  | 2 | 0 | complete | 182 | 2025-12-29
189 | 2025-12-15 | 178192 | Fuel Water Separator | 320/A7124 | BoomLoader | Merlo | P27 |  | 2 | Nos |  | 2 | 0 | complete | 182 | 2025-12-29
190 | 2025-12-15 | 178192 | Bolt with nut | 5/16*3 inch |  |  |  |  | 15 | Nos |  | 15 | 0 | complete | 180 | 2025-12-29
191 | 2025-12-15 | 178192 | Bolt with nut | 3/8*3 inch |  |  |  |  | 15 | Nos |  | 0 | 15 | left
192 | 2025-12-15 | 178192 | Bolt with nut with washer | 10mm*3inch |  |  |  |  | 20 | Nos |  |  | 20 | left
193 | 2025-12-15 | 178192 | Oil filter | 2654403 | Genarator | Perkins | JP 60 |  | 2 | Nos |  | 2 | 0 | complete | 180 | 2025-12-29
194 | 2025-12-15 | 178192 | Fuel filter | 4461492 | Genarator | Perkins | JP 60 |  | 2 | Nos |  | 2 | 0 | complete | 180 | 2025-12-29
195 | 2025-12-15 | 178192 | Fuel Water Separator |  | Genarator | Perkins | JP 60 |  | 2 | Nos | 13030 6360 | 2 | 0 | complete | 180 | 2025-12-29
196 | 2025-12-20 | 178822 | Boom Grease | [5 empty] | 5 | KG | 4003/4005 | 5 | 0 | complete | 194 | 2026-01-03
197 | 2025-12-20 | 178822 | Fan belt | [5 empty] | 1 | Nos |  | 1 | 0 | complete | 196 | 2026-01-10
198 | 2025-12-20 | 178822 | Air Stem valve core | [5 empty] | 10 | Nos |  | 100 | -90 | exceed | 47 | 2026-01-03
199 | 2025-12-17 | 800 |  |  | 1.5 Ton Pickup | Toyto | Hilux | 27674 | 1 | Nos |  | 1 | 0 | Arrivel Date | 176 | 2025-12-17
200 | 2025-12-17 | 800 |  |  | 1.5 Ton Pickup | Toyto | Hilux | 27675 | 1 | Nos |  | 1 | 0 | Arrivel Date | 176 | 2025-12-17
201 | 2025-12-17 | 800 |  |  | 1.5 Ton Pickup | Toyto | Hilux | 27672 | 1 | Nos |  | 1 | 0 | Arrivel Date | 176 | 2025-12-17
202 | 2025-12-17 | 800 |  |  | 1.5 Ton Pickup | Toyto | Hilux | 27643 | 1 | Nos |  | 1 | 0 | Arrivel Date | 176 | 2025-12-17
203 | 2025-12-17 | 800 |  |  | 1.5 Ton Pickup | Toyto | Hilux | 27671 | 1 | Nos |  | 1 | 0 | Arrivel Date | 176 | 2025-12-17
204 | 2025-12-20 | 178822 | Side Mirror |  | Skid Steer Loader | Case | SR130B | 292.089 | 1 | Nos |  | 1 | 0 | complete | 180 | 2025-12-29
205 | 2025-12-26 | 178706 | Floor mat |  | 1.5 Ton Pickup | Toyto | Hilux | 44138 | 1 | Nos |  | 1 | 0 | complete | 196 | 2026-01-10
206 | 2025-12-26 | 178706 | Floor mat |  | 1.5 Ton Pickup | Toyto | Hilux | 27675 | 1 | Nos |  | 1 | 0 | complete | 196 | 2026-01-10
207 | 2025-12-26 | 178706 | Floor mat |  | 1.5 Ton Pickup | Toyto | Hilux | 27672 | 1 | Nos |  | 1 | 0 | complete | 196 | 2026-01-10
208 | 2025-12-26 | 178706 | Floor mat |  | 1.5 Ton Pickup | Toyto | Hilux | 27643 | 1 | Nos |  | 1 | 0 | complete | 196 | 2026-01-10
209 | 2025-12-26 | 178706 | Floor mat |  | 1.5 Ton Pickup | Toyto | Hilux | 27671 | 1 | Nos |  | 1 | 0 | complete | 196 | 2026-01-10
210 | 2025-12-26 | 178706 | Floor mat |  | 1.5 Ton Pickup | Toyto | Hilux | 27678 | 1 | Nos |  | 1 | 0 | complete | 196 | 2026-01-10
211 | 2025-12-26 | 178706 | Floor mat |  | 1.5 Ton Pickup | Toyto | Hilux | 27674 | 1 | Nos |  | 1 | 0 | complete | 196 | 2026-01-10
212 | 2025-11-19 | 178120 | 4M16 Anchor Bolt With Boom Embedment Depth | [5 empty] | 40 | Nos | 16 MM L Type Anchor Bolt with nut and Washer 50 kg | 40 | 0 | complete | 138 | 2025-12-22
213 | 2025-11-19 | 178120 | M16 Nut | [5 empty] | 80 | Nos |  |  | 80 | left
214 | 2025-11-19 | 178120 | M16 Washer | [5 empty] | 80 | Nos |  |  | 80 | left
215 |  | 853 |  |  | MEWP | Lingong | AR24J |  | 1 | Nos |  | 1 | 0 | Arrivel Date |  | 2025-12-31
216 |  | 853 |  |  | MEWP |  | sx-125 xc | Bx 125D -2024/ BG 08606 | 1 | Nos |  | 1 | 0 | Arrivel Date |  | 2026-01-01
217 |  | 806 |  |  | Skid Steer Loader | Case | SR130B |  | 1 | Nos |  | 1 | 0 | Arrivel Date | 186 | 2026-01-02
218 |  | 806 |  |  | Skid Steer Loader | Case | SR130B |  | 1 | Nos |  | 1 | 0 | Arrivel Date | 186 | 2026-01-02
219 |  | 810 |  |  | Mobile crane | XCMG | 60 T | 201.039 | 1 | Nos |  | 1 | 0 | Arrivel Date | 188 | 2026-01-02
220 |  | 810 |  |  | Mobile crane | XCMG | 60 T | 201.036 | 1 | Nos |  | 1 | 0 | Arrivel Date | 192 | 2026-01-03
221 | 2026-01-03 | 178704 | IVMS installation |  | HIAB |  |  | 25306 | 1 | Nos |  |  | 1 | Services
222 | 2026-01-07 | 178708 | Fan v Belt | Aux-10x 950k | Tower Light | Trex |  | 191.124 | 3 | Nos | 10x 950 | 3 | 0 | complete | 208 | 2026-01-23
223 | 2026-01-07 | 178708 | Fan v Belt | Aux-10x 950k | Tower Light | Trex |  | 191.125 | 3 | Nos | 10x 950 | 3 | 0 | complete | 208 | 2026-01-23
224 | 2026-01-07 | 178708 | Filter Kit |  | Back hoe Loader | JCB | 3 DX | 191.315 | 1 | Nos |  | 1 | 0 | complete | 200 | 2026-01-13
225 | 2026-01-07 | 178708 | OIL filter |  | Genarator | Perkins |  | 191.315 | 3 | Nos |  | 3 | 0 | complete | 202 | 2026-01-22
226 | 2026-01-07 | 178708 | Fuel Filter |  | Genarator | Perkins |  | 191.315 | 3 | Nos | 4461492 | 3 | 0 | complete | 212 | 2026-01-27
227 | 2026-01-07 | 178708 | Air Filter |  | Genarator | Perkins |  | 191.422 | 1 | Nos | 26510337 | 1 | 0 | complete | 212 | 2026-01-27
228 | 2026-01-07 | 178710 | Floor mat |  | 4.2 ton Pick up | Mitsubishi |  | 191.427 | 1 | Nos |  | 1 | 0 | complete | 236 | 2026-02-21
229 | 2026-01-10 | 178712 | Radiator tank |  | BoomLoader | Merlo | P27 | 191.124 | 1 | Nos | 332/E9125 | 1 | 0 | complete | 204 | 2026-01-22
230 | 2026-01-13 | 178714 | Oprator cabin fan |  | Skid Steer Loader | Case | SR130B | 191.125 | 1 | Nos |  | 1 | 0 | complete | 212 | 2026-01-27
231 | 2026-01-13 | 178714 | Wire rope spray |  | Mobile crane | XCMG |  | 191.125 | 12 | Nos |  |  | 12 | left
232 | 2026-01-13 | 178714 | EP 2 Greaese |  |  |  |  | 191.315 | 15 | KG |  |  | 15 | left
233 | 2026-01-13 | 178714 | Center Mirror |  | Skid Steer Loader | Case | SR130B | 292.101 | 1 | Nos |  | 1 | 0 | complete | 204 | 2026-01-22
234 | 2026-01-13 | 178714 | Center Mirror |  | Skid Steer Loader | Case | SR130B | 292.104 | 1 | Nos |  | 1 | 0 | complete | 204 | 2026-01-22
235 | 2026-01-13 | 178714 | Center Mirror |  | Skid Steer Loader | Case | SR130B | 292.089 | 1 | Nos |  | 1 | 0 | complete | 204 | 2026-01-22
236 | 2026-01-14 | 178716 | METAL HALIDE LAMP | MH1000/U/MGOG BT37 | Diesel Tower Light | RL 4000 |  | 197.124 | 3 | Nos |  | 3 | 0 | complete | 212 | 2026-01-27
237 | 2026-01-14 | 178716 | venture high intencity discharge venture metal halide | Grease adapter (Farid) |  |  |  |  | 3 | Nos |  | 3 | 0 | complete | 208 | 2026-01-23
238 | 2026-01-14 | 178718 | Wiper Blade | ALL Season(Good Quality) | Car | Nissan |  | 92323 | 1 | Set | Y-159-18(Small piece) &y-159-26 | 1 | 0 | Returned | 58 | 2026-02-03 | 22 | 2026-02-11
239 | 2026-01-14 | 178718 | Wiper Blade | ALL Season(Good Quality) | Car | Nissan |  | 93347 | 1 | Set | Y-159-18(Small piece) &y-159-26 | 1 | 0 | Returned | 58 | 2026-02-03 | 22 | 2026-02-11
240 | 2026-01-14 | 178718 | Wiper Blade | ALL Season(Good Quality) | Car | Nissan |  | 61392 | 1 | Set | Y-159-18(Small piece) &y-159-26 | 1 | 0 | Returned | 58 | 2026-02-03 | 22 | 2026-02-11
241 | 2026-01-14 | 178718 | Wiper Blade | ALL Season(Good Quality) | Car | Nissan |  | 61394 | 1 | Set | Y-159-18(Small piece) &y-159-26 | 1 | 0 | Returned | 58 | 2026-02-03 | 22 | 2026-02-11
242 | 2026-01-14 | 178718 | Wiper Blade | ALL Season(Good Quality) | Car | Nissan |  | 61402 | 1 | Set | Y-159-18(Small piece) &y-159-26 | 2 | -1 | Returned | 58 | 2026-02-03 | 22 | 2026-02-11
243 |  | 4202252 | Pully block |  | Mobile crane | XCMG |  | 286.036 | 1 | Nos |  | 1 | 0 | complete | 198 | 2026-01-10
244 | 2025-10-27 | 234 |  |  | BoomLoader | Merlo | P27 | 290.029 | 1 | Nos |  | 1 | 0 | Arrivel Date | 140 | 2025-10-27
248 |  | 178806 | hose A/C |  |  | Mitsubishi |  |  | 1 | Nos |  | 1 | 0 | complete | 180 | 2025-12-29
249 |  | 610 | Diesel Fitting gun | [5 empty] | 1 | Nos |  | 1 | 0 | complete | 184 | 2025-12-29
250 | 2026-01-19 | 178722 | Left side Lock Assembly with key |  | unit | Benz | Actros | 76953 | 1 | Nos |  | 1 | 0 | complete | 240 | 2026-03-06
251 | 2026-01-19 | 178724 | RCI/ASLI/LMI verification certificate for mobile crane | Lifting Equipment | Crane | Sany | 60 T | 286.036 | 1 | Nos |  |  | 1 | Services
252 | 2026-01-19 | 178724 | RCI/ASLI/LMI verification certificate for mobile crane | Lifting Equipment | Crane | Sany | 60 T | 286.039 | 1 | Nos |  |  | 1 | Services
258 | 2026-01-22 | 178906 | pneumatic grease PUMP with hose rail | [5 empty] | 1 | Nos |  |  | 1 | left
259 | 2026-01-22 | 178906 | Penumatic grease pump (Engine oil, hydrolic oil) | [5 empty] | 2 | Nos |  |  | 2 | left
260 | 2026-01-24 | 178726 | Diesel Hose | 2026-04-01 |  |  |  |  | 5 | M |  |  | 5 | left
261 | 2026-01-24 | 178726 | Diesel Hose | 2016-04-01 |  |  |  |  | 5 | M |  |  | 5 | left
262 | 2026-01-24 | 178726 | Diesel Hose | 2026-06-03 |  |  |  |  | 5 | M |  |  | 5 | left
263 | 2026-01-24 | 178726 | Diesel Hose | 2026-02-01 |  |  |  |  | 5 | M |  |  | 5 | left
264 | 2026-01-24 | 178726 | Diesel Hose | 2026-06-05 |  |  |  |  | 5 | M |  |  | 5 | left
265 | 2026-01-24 | 178726 | Diesel Hose | 2026-04-03 |  |  |  |  | 5 | M |  |  | 5 | left
266 | 2026-01-24 | 178726 | Diesel Hose | 2026-08-07 |  |  |  |  | 5 | M |  |  | 5 | left
267 | 2026-01-24 | 178726 | Diesel Hose | 1 |  |  |  |  | 5 | M |  |  | 5 | left
268 | 2026-01-24 | 178726 | Jubliee Hose Clamp | 1 |  |  |  |  | 1 | Nos |  |  | 1 | left
269 |  | 225 | Generator and Dip Tray | 44 kw | Genarator | Weichai | HP 50 | 191.422 | 1 | Nos |  | 1 | 0 | Arrivel Date | 210 | 2026-01-26
270 |  | 255 | Generator and Dip Tray | 30 kw | Genarator | Weichai | HP 50 | 191.427 | 1 | Nos |  | 1 | 0 | Arrivel Date | 210 | 2026-01-26
271 | 2026-01-22 | 178720 | Oil filter | 3795700 | Roller Compactor |  |  | 191.124 | 3 | Nos |  |  | 3 | left
272 | 2026-01-22 | 178720 | Fuel filter | 40089401 | Roller Compactor |  |  | 191.125 | 3 | Nos |  |  | 3 | left
273 | 2026-01-22 | 178720 | Air filter(Outer) | 4030101 | Roller Compactor |  |  | 191.125 | 3 | Nos |  |  | 3 | left
274 | 2026-01-22 | 178720 | Oil filter | SP 937 | Tower Light |  |  | 191.315 | 3 | Nos | LF 940 | 3 | 0 | complete | 216 | 2026-02-03
275 | 2026-01-22 | 178720 | Fuel filter | BF 940 | Tower Light |  |  | 191.125 | 3 | Nos | FF526 | 3 | 0 | complete | 216 | 2026-02-03
276 | 2026-01-22 | 178720 | Air filter(Outer) | 121911138 | Tower Light |  |  | 191.125 | 3 | Nos |  |  | 3 | left
277 | 2026-01-27 | 178728 | Oil filter | 6675517 | Bobcat |  |  | 191.315 | 3 | Nos |  | 3 | 0 | complete | 234 | 2026-02-17
278 | 2026-01-27 | 178728 | Air filter(Inner) | 6666376 | Bobcat |  |  | 207.104 | 3 | Nos |  |  | 3 | left
279 | 2026-01-27 | 178728 | Air filter(Outer) | c14210/2 |  |  |  | 191.315 | 1 | Nos | 26510337 | 3 | -2 | exceed | 60 | 2026-02-09
280 | 2026-01-27 | 178728 | Pevnatic Quick Releace Cuoling | 1/2 inch & 17 mm | [5 empty] | Nos |  |  | 0 | left
281 | 2026-01-28 | 178730 | IVMS installation |  | SUV | Toyato | Land Cruisser | 72889 | 1 | Nos |  |  | 1 | left
282 | 2026-01-28 | 178732 | Starter Motor coil complete assembly |  | Tower Light | Trex | RL 4000 |  | 1 | Nos |  | 1 | 0 | complete | 220 | 2026-02-09
283 | 2026-01-29 | 178734 | Engine Oil | 15w/40 |  |  |  |  | 1 | Nos |  | 1 | 0 | complete | 218 | 2026-02-05
284 | 2026-01-29 | 178734 | Rust of spray | WD/40 |  |  |  |  | 12 | Nos | RS 20 | 12 | 0 | complete | 218 | 2026-02-05
285 | 2026-01-29 | 178736 | Rack For mechanical Work shop | [5 empty] | 2 | Nos | Recived in pices |  | 2 | complete | 144 | 2026-02-11
286 | 2026-01-31 | 178738 | Mechanic work bench | [5 empty] | 1 | Nos | 90 CM*120 CM*90 CM | 1 | 0 | Arrivel Date | 146 | 2026-02-19
287 | 2026-02-04 | 178934 | Front wind shield |  |  | Nissan | Path finder | 93262 | 1 | Nos | CHANGED AT MUSSAFAH | 1 | 0 | complete |  | 2026-02-10
288 |  | 854 |  | 24 M | MEWP | LGMG | AR 24 J | ZG06820 | 1 | Nos |  | 1 | 0 | Arrivel Date |  | 2026-02-05
289 | 2026-02-06 | 178742 | fog light front |  | 4.2 ton Pick up | Fuso | Canter | 31545 | 2 | Nos | HL 225 | 2 | 0 | complete | 230 | 2026-02-16
290 | 2026-02-06 | 178742 | fog light Rear |  | 4.2 ton Pick up | Fuso | Canter | 31545 | 2 | Nos | FL 6524 | 2 | 0 | complete | 230 | 2026-02-16
291 | 2026-02-06 | 178742 | Beacon light |  | 4.2 ton Pick up | Fuso | Canter | 31545 | 1 | Nos |  | 2 | -1 | exceed | 68 | 2026-02-21
292 | 2026-02-09 | 178744 | Filter kit |  | Bobcat | Bobcat | 450 S | 292.101 | 1 | Nos |  | 1 | 0 | complete | 234 | 2026-02-17
293 | 2026-02-09 | 178744 | Filter kit |  | Bobcat | Bobcat | 450 S | 292.104 | 1 | Nos |  | 1 | 0 | complete | 234 | 2026-02-17
294 | 2026-02-09 | 178744 | Cabin fan |  | Bobcat | Bobcat | 450 S | 292.101 | 1 | Nos | 20240901 | 1 | 0 | complete | 230 | 2026-02-16
295 | 2026-02-09 | 178744 | Cabin fan |  | Bobcat | Bobcat | 450 S | 292.104 | 1 | Nos | 20240901 | 1 | 0 | complete | 230 | 2026-02-16
296 |  | 865 | Service kit |  |  | XCMG |  |  | 2 | Nos |  | 2 | 0 | Arrivel Date |  | 2026-02-03
297 | 2026-02-10 | 178746 | Oil filter | 15613-EVO52 | unit | Benz | Actros | 76953 | 3 | Nos |  | 3 | 0 | complete | 240 | 2026-03-06
298 | 2026-02-10 | 178746 | Oil filter | 15613 - EVO43 | unit | Benz | Actros | 76953 | 3 | Nos | 15613EV052 | 1 | 2 | left | 70 | 2026-03-06
299 | 2026-02-10 | 178746 | Fuel filter | 23304 - Ev 351 | unit | Benz | Actros | 76953 | 3 | Nos | 156072261 | 3 | 0 | complete | 240 | 2026-03-06
300 | 2026-02-10 | 178746 | Air filter(Inner) | 17801 - EW060 | unit | Benz | Actros | 76953 | 3 | Nos | 178013450 | 3 | 0 | complete | 240 | 2026-03-06
301 | 2026-02-10 | 178746 | Air filter(Outer) | 17 801 - EW 050 | unit | Benz | Actros | 76953 | 3 | Nos |  | 3 | 0 | complete | 240 | 2026-03-06
302 | 2026-02-10 | 178746 | Fuel Water Separator | 23304 -EV140 | unit | Benz | Actros | 76953 | 3 | Nos |  | 3 | 0 | complete | 240 | 2026-03-06
303 | 2026-01-07 | 178708 | Filter Kit |  | Back hoe Loader | JCB | 3 DX | 290.018 | 1 | Nos |  | 1 | 0 | complete | 222 | 2026-02-10
305 | 2026-02-12 | 850 |  |  | Air compressor | ATLAS COPCO | T250-7 | 190.11 | 1 | Nos |  | 1 | 0 | Arrivel Date | 224 | 2026-02-12
306 | 2026-02-12 | 850 |  |  | Air compressor | ATLAS COPCO | T250-7 | 190.111 | 1 | Nos |  | 1 | 0 | Arrivel Date | 224 | 2026-02-12
307 | 2026-02-12 | 850 |  |  | Air compressor | Chicago Pneumatic | CPS370-150 | 190.114 | 1 | Nos |  | 1 | 0 | Arrivel Date | 224 | 2026-02-12
308 | 2026-02-03 | 851 |  |  | Genarator | Weichai | HP 250 | 191.458 | 1 | Nos |  | 1 | 0 | Arrivel Date | 228 | 2026-02-16
309 | 2026-02-03 | 851 |  |  | Genarator | Weichai | HP 250 | 191.459 | 1 | Nos |  | 1 | 0 | Arrivel Date | 228 | 2026-02-16
310 | 2026-02-03 | 851 |  |  | Genarator | Weichai | HP 30 | 191.428 | 1 | Nos |  | 1 | 0 | Arrivel Date | 228 | 2026-02-16
311 | 2026-02-16 | 851 | 37 |  | Genarator | Perkins | JP 12.5 | 191.254 | 1 | Nos |  | 1 | 0 | Arrivel Date | 226 | 2026-02-16
312 | 2026-01-14 | 178718 | Wiper Blade | ALL Season(Good Quality) | Car | Nissan |  | 92323 | 1 | Set | Y-159-18(Small piece) &y-159-26 | 1 | 0 | complete | 230 | 2026-02-16
313 | 2026-01-14 | 178718 | Wiper Blade | ALL Season(Good Quality) | Car | Nissan |  | 93347 | 1 | Set | Y-159-18(Small piece) &y-159-26 | 1 | 0 | complete | 230 | 2026-02-16
314 | 2026-01-14 | 178718 | Wiper Blade | ALL Season(Good Quality) | Car | Nissan |  | 61392 | 1 | Set | Y-159-18(Small piece) &y-159-26 | 1 | 0 | complete | 230 | 2026-02-16
315 | 2026-01-14 | 178718 | Wiper Blade | ALL Season(Good Quality) | Car | Nissan |  | 61394 | 1 | Set | Y-159-18(Small piece) &y-159-26 | 1 | 0 | complete | 230 | 2026-02-16
316 | 2026-01-14 | 178718 | Wiper Blade | ALL Season(Good Quality) | Car | Nissan |  | 61402 | 1 | Set | Y-159-18(Small piece) &y-159-26 | 2 | -1 | complete | 230 | 2026-02-16
317 | 2026-02-21 | 178748 | Break Valve |  | unit | Benz | Actros | 76953 | 1 | Nos |  |  | 1 | left
318 | 2026-02-23 | 178964 | Boom Grease | Adnoc grease |  |  |  |  | 1 | Nos |  |  | 1 | left
319 | 2026-02-24 | 178750 | Third Party |  | unit | Benz | Actros | 76953 | 1 | Nos |  |  | 1 | Services
320 | 2026-02-24 | 178750 | Third Party |  | Trailer |  | 12589 |  | 1 | Nos |  |  | 1 | Services
321 | 2026-02-24 | 178750 | Third Party |  | unit | Scania | XT Range |  | 1 | Nos |  |  | 1 | Services
322 | 2026-02-24 | 178750 | Third Party |  | Trailer |  | 30029 |  | 1 | Nos |  |  | 1 | Services
323 | 2026-02-25 | 178752 | Third Party |  | Fork lift |  |  | 28533 | 1 | Nos |  |  | 1 | Services
324 | 2026-02-24 | 178754 | Ivms Installation |  | 1.5 Ton Pickup | Toyto | Hilux | 19556 | 1 | Nos |  |  | 1 | Services
325 |  | 852 |  |  | Mobile crane | XCMG | 90 T | 286.037 | 1 | Nos |  | 1 | 0 | Arrivel Date | 284 | 2026-03-08
326 |  | 852 |  |  | Crawler crane | XCMG | 75 T | 286.044 | 1 | Nos |  | 1 | 0 | Arrivel Date | 238 | 2026-02-27